## Sheet1
Team A Project Plan
TASK FOCUS |  | TASK LETTER | TASK DESCRIPTION | DATE START |  | DATE END | PREDECESSOR TASK(s) | RESOURCE(s)
Database
|  | A | Create Database | 2021-06-21 |  | 2021-06-28 |  | Isaak Galle
|  | B | Create Stored Procedures | 2021-06-29 |  | 2021-07-05 | A | Isaak Galle
|  | C | Populate With Test Data | 2021-07-06 |  | 2021-07-12 | B | Isaak Galle
| Software Development | [6 empty] | View | Model | Controller
|  | D | Create Main Page | 2021-06-21 |  | 2021-06-28 |  | Kaitlin Cordell | Brandon Wernke | Omonigho Odairi
|  | D-2 | Create Recipe API Connection | 2021-06-25 |  | 2021-06-28 | D |  |  | Brandon Wernke
|  | F | Create Login Page | 2021-06-29 |  | 2021-07-05 | B, A | Kaitlin Cordell | Brandon Wernke | Omonigho Odairi
|  | G | Create Account Management Page | 2021-07-06 |  | 2021-07-12 | F | Kaitlin Cordell | Brandon Wernke | Omonigho Odairi
|  | H | Create Shopping List Pages | 2021-07-13 |  | 2021-07-19 | D, E, F | Kaitlin Cordell | Brandon Wernke, Isaak Galle | Omonigho Odairi
|  | I | Create API Connection with Kroger | 2021-07-20 | 5 weeks | 2021-07-26 | H |  |  | Brandon Wernke, Isaak Galle
Unit Test
|  | J | Test Main Page | 2021-06-29 |  | 2021-07-05 | D | Kaitlin, Brandon
|  | K | Test Login Page | 2021-07-06 |  | 2021-07-12 | E | Omoh, Isaak
|  | L | Test Search Functions | 2021-07-13 |  | 2021-07-19 | F | Kaitlin, Brandon
|  | M | Test Shopping List Pages | 2021-07-20 |  | 2021-07-26 | H | Omoh, Isaak
|  | N | Test Kroger Functionality | 2021-07-27 | 5 weeks | 2021-08-02 | I | Kaitlin, Brandon
User Tests
|  | O | Develop Test Plan | 2021-07-27 |  | 2021-08-02 | N | Team
|  | P | Conduct User Test with users | 2021-08-03 |  | 2021-08-09 | O | Team
Presentation Development
|  | Q | Develop Presentation | 2021-08-10 |  | 2021-08-12 | A .. P | Team
|  | R | Practice Presentation | 2021-08-12 |  | 2021-08-12 | Q | Team
Present Project
|  | TASK LETTER | Present Project | 2021-08-19 |  | 2021-08-19 | R | Team